## DASHBOARD
ICOWASH PROJECT
Report #:
LOT 1:
DATE: PREPARED BY:
Progress of total work done Progress of TOTAL work done
Total Rate of completion |  | 33.33%
Total Ongoing |  | 0%
Total Not Started |  | 66.67%
Notes:

## Details
ICOWASH PROJECT
| 0 |  |  | Report #:
0
LOT 1:
DATE: PREPARED BY:
S/N | District | Community | Name of Institution | Facility | Number of facilities | GPS Coordinates |  | Hydrogeological Investigations |  |  |  | Drilling and construction | [10 empty] | Pumping test | [7 empty] | Water Quality |  |  |  | Platform construction |  |  |  | Pump installation, disinfection and caretaker training |  |  |  |  | Total % Completed | Total % Ongoing | Total % Not started
[6 empty] | Latitude | Longitude | Status | Start date | End date | Comments | Status | Start date | End date | Overburden (m) | Hard rock (m) | Total Depth (m) | Airlift yield (l/min) | Screen sections (m) | Screen length (m) | Plain length (m) | Borehole Status (Wet, Marginal, Dry) | Status | Start date | End date | Pump Setting (m) | Static Water Level (m) | Pumping Test Yield (l/min) | Dynamic Water Level after 6 hours pumping (m) | Recovery depth after 3 hours (m) | Status | Start date | End date | Comments | Status | Start date | End date | Comments | Status | Start date | End date | Hand pump type | Comments
1 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
2 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
3 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
4 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
5 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
6 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
7 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
8 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
9 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
10 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
11 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
12 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
13 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
14 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
15 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
16 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
17 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
18 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
19 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
20 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
21 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
22 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
23 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
24 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
25 | [7 empty] | Completed |  |  |  | completed |  |  |  |  | 0 | [5 empty] | Not started | [7 empty] | Not started |  |  |  | Not started |  |  |  | Not started |  |  |  |  | 33.33% | 0% | 66.67%
|  |  |  | TOTAL | 0 | [37 empty] | Average | 33.33% | 0% | 66.67%