## Slide 1
Photo by Oscar Leiva/Silverlight for CRS

## Slide 2: Planning Timeline
Nov. 20, 2023: Last day to decrease or cancel orders.
Jan. 2-10, 2024: Existing orders ship.
Feb. 14, 2024: Ash Wednesday.
March 15, 2024: Last day orders can be placed to arrive by Easter.
March 31, 2024: Easter Sunday.
Aug. 31, 2024: Lent 2024 Revenue Reporting Form and diocesan remittance due to CRS.

## Slide 3: November 2023
CRS will review donations for Rice Bowl 2023 sent directly to CRS with the information on your Revenue Reporting Form. If more than 75% of the total gifts from your diocese have been received by CRS, we will send you a check to add to the 25% retained for local use. Checks are usually mailed in December and January.
Review the 25% Guidelines at crsricebowl.org/diocese.
See what’s new with CRS Rice Bowl by visiting crsricebowl.org.

## Slide 4: December 2023
The promotion kit is mailed to diocesan directors in all participating dioceses.
  Contains tips for promotion, including samples of materials. You can also find resources online at crsricebowl.org/diocese.
Recruit volunteers to help you contact parishes and schools. Encourage them to participate in CRS Rice Bowl.
Nov. 20, 2023: Last chance to cancel/reduce orders—materials are packed late November! Materials can always be ordered or increased.

## Slide 5: December 2023
Ensure all parishes and schools in your diocese have placed their orders for free CRS Rice Bowl materials. To order materials:
  Call 800-222-0025.
  Visit crsricebowl.org/order.
Ask your bishop to review and adapt the Bishop’s Endorsement Letter to be sent to faith communities. This can be found at crsricebowl.org/diocese.

## Slide 6: January 2024
This year’s materials are shipped to parishes and schools between Jan. 2 and Jan. 10, 2024. Orders may still be placed throughout the Lenten season!
Host a CRS Rice Bowl information session for CRS Rice Bowl coordinators.
  Show the “How to Kick Off CRS Rice Bowl” video on crsricebowl.org/parishes.
Place a CRS Rice Bowl web banner on your diocesan website or include an ad in your diocesan paper. These can be found at crsricebowl.org/diocese.

## Slide 7: February 2024
In-Person Activities
Encourage CRS Rice Bowl coordinators to ensure each family receives a CRS Rice Bowl. Ash Wednesday is February 14, 2024!
Host a CRS Rice Bowl kickoff event in your diocese. Take photos and use #CRSRiceBowl and #CRSPlatodeArroz on social media channels.
If you cannot distribute CRS Rice Bowls, coordinators can encourage families to visit crsricebowl.org/families to print a DIY CRS Rice Bowl label.

## Slide 8: March 2024
Remind organizations and coordinators of Holy Week resources available at crsricebowl.org/holy-week and crsplatodearroz.org/semana-santa.
Refer CRS Rice Bowl coordinators to the video, “How to Collect CRS Rice Bowls,” for tips on hosting a prayerful CRS Rice Bowl collection.

## Slide 9: April 2024
CRS will mail a “Turn in your CRS Rice Bowls” packet to parishes and schools that ordered materials. This includes information on how to collect contributions and return them to their diocesan office. This can also be found on the CRS Rice Bowl parish or Grades 1-8 website. Ensure parishes and schools receive this packet and know where they should send their donations.
Ask your bishop to adapt and send the Bishop’s Thank You Letter.
Post a diocesan Thank You Ad on your diocesan website or paper. The ad can be found at crsricebowl.org/dioceses.

## Slide 10: May/June 2024
Review revenue reporting and remittance instructions.
CRS will send an email with information on the 2024 Revenue Reporting Form. Information can also be found at crsricebowl.org/revenue.

## Slide 11: August 2024
Publish your diocese’s total donation amount in your diocesan newspaper. Be sure to highlight where your local 25% is used!
By August 31:
  Submit the completed Revenue Reporting Form at http://ricebowl.crs.org/.
  Send 75% of your diocese’s donation to:
Catholic Relief Services—CRS Rice Bowl
PO Box 5200
Harlan, IA 51593-4700

## Slide 12: September 2024
For DD-designated dioceses:
Order Updated Spreadsheets are due November 1.
For IND-designated dioceses (dioceses where parishes and schools update their orders directly with CRS):
A postcard is mailed to parishes and schools at the end of September, encouraging them to update their order for 2025 CRS Rice Bowl materials.
Not sure if you’re IND or DD? Contact crsricebowl@crs.org.

## Slide 13: Thank you!